## Sheet1
| Start Date | End Date | Timeline | Status | Member(s)
Buliding a Neural Network | 2019-11-18 | 2020-03-06 |  | Active
Functional Specification | 2019-11-18 | 2019-12-06 |  | Active | Janesh, Paul
Build first simple neural network | 2019-12-09 | 2019-12-22 |  | Upcoming | Janesh
Obtain and parse data | 2019-12-09 | 2019-12-22 |  | Upcoming | Paul
Develop a trading strategy for stocks | 2019-12-09 | 2019-12-15 |  | Upcoming | Janesh, Paul
Deep Feed Foward(DFF) Network | 2020-01-20 | 2020-02-02 |  | Upcoming | Janesh, Paul
Reccurant Neural Network | 2020-01-20 | 2020-02-02 |  | Upcoming | Janesh, Paul
Complete LSTM model | 2020-02-17 | 2020-03-01 |  | Upcoming | Janesh
User Interface | 2020-02-17 | 2020-03-01 |  | Upcoming | Paul
Testing and Submission | 2020-03-02 | 2020-03-06 |  | Upcoming | Janesh, Paul
Overall Progress